## Requirements RTM
Project 4 — Requirements Traceability Matrix
Closed-Loop Specialty Referral Management ¦ Synthetic portfolio implementation
Requirement ID | Type | Priority | Requirement | Acceptance Criterion | Planned Evidence | Verification Method | Implementation Status | Test Status | Evidence Path / Link | Owner | Notes
BR-001 | Business | Must | NorthStar shall use one standardized enterprise referral-status model. | Every referral status maps to an approved value with documented entry and exit conditions. | Workflow design; KPI specification; UAT | Review + UAT | Not Started | Not Tested |  | Brandon McDermott
BR-002 | Business | Must | Every active referral shall have an accountable owner or operational queue. | A query returns zero active referrals lacking both an owner and valid queue, except documented interface exceptions. | Workflow design; KPI specification; UAT | Review + UAT | Not Started | Not Tested |  | Brandon McDermott
BR-003 | Business | Must | The organization shall distinguish referral scheduling, encounter completion, report receipt, and clinical closure. | The data model and workflow contain separate fields or events for all four milestones. | Workflow design; KPI specification; UAT | Review + UAT | Not Started | Not Tested |  | Brandon McDermott
BR-004 | Business | Must | Urgent and overdue referrals shall be distinguishable from routine work. | Users can retrieve an urgent or overdue queue using defined priority and service-level logic. | Workflow design; KPI specification; UAT | Review + UAT | Not Started | Not Tested |  | Brandon McDermott
BR-005 | Business | Must | Referral closure shall use standardized completed and non-completed criteria. | Every closed referral satisfies completed closure rules or contains an approved non-completion or cancellation reason. | Workflow design; KPI specification; UAT | Review + UAT | Not Started | Not Tested |  | Brandon McDermott
BR-006 | Business | Must | Leadership shall be able to evaluate referral performance across the lifecycle. | The dashboard reports intake, outreach, scheduling, completion, report receipt, closure, and aging metrics. | Workflow design; KPI specification; UAT | Review + UAT | Not Started | Not Tested |  | Brandon McDermott
BR-007 | Business | Should | Site and specialty performance shall be comparable using governed definitions. | The same metric logic applies to all sites and specialties, with documented exclusions. | Workflow design; KPI specification; UAT | Review + UAT | Not Started | Not Tested |  | Brandon McDermott
BR-008 | Business | Must | The implementation shall preserve human review for clinical priority and clinical escalation. | No automated process independently assigns or changes clinical urgency without an authorized user action. | Workflow design; KPI specification; UAT | Review + UAT | Not Started | Not Tested |  | Brandon McDermott
FR-001 | Functional | Must | The system shall create a unique internal referral record for every accepted source referral. | Each loaded referral has a non-null unique internal identifier and retained source identifier. | Configuration workbook; SQL/Python logic; UAT | Functional test + UAT | Not Started | Not Tested |  | Brandon McDermott
FR-002 | Functional | Must | The system shall record the source system and referral-received timestamp. | Both values are populated for at least 99% of accepted referrals; exceptions are reported. | Configuration workbook; SQL/Python logic; UAT | Functional test + UAT | Not Started | Not Tested |  | Brandon McDermott
FR-003 | Functional | Must | The system shall validate required patient, provider, clinical, payer, specialty, priority, and document fields. | Each referral receives a validation result and a structured list of blocking failures. | Configuration workbook; SQL/Python logic; UAT | Functional test + UAT | Not Started | Not Tested |  | Brandon McDermott
FR-004 | Functional | Must | Referrals with blocking validation failures shall enter `Needs Information`. | A deliberately incomplete test referral is routed to the correct status and queue. | Configuration workbook; SQL/Python logic; UAT | Functional test + UAT | Not Started | Not Tested |  | Brandon McDermott
FR-005 | Functional | Must | Authorized users shall be able to resolve validation failures. | After required corrections, the referral passes validation and advances without losing its history. | Configuration workbook; SQL/Python logic; UAT | Functional test + UAT | Not Started | Not Tested |  | Brandon McDermott
FR-006 | Functional | Should | Authorized users may override selected nonclinical validation rules with a reason. | An override requires user, timestamp, rule, and explanatory reason. | Configuration workbook; SQL/Python logic; UAT | Functional test + UAT | Not Started | Not Tested |  | Brandon McDermott
FR-007 | Functional | Should | The system shall identify possible duplicate active referrals. | A configured duplicate test case is flagged without being automatically deleted. | Configuration workbook; SQL/Python logic; UAT | Functional test + UAT | Not Started | Not Tested |  | Brandon McDermott
FR-008 | Functional | Must | The system shall assign complete referrals to an owner or accountable queue. | Every referral leaving intake has a valid assignment. | Configuration workbook; SQL/Python logic; UAT | Functional test + UAT | Not Started | Not Tested |  | Brandon McDermott
FR-009 | Functional | Must | Assignment rules shall consider at least location, specialty, and priority. | Test referrals with different combinations route to their expected queues. | Configuration workbook; SQL/Python logic; UAT | Functional test + UAT | Not Started | Not Tested |  | Brandon McDermott
FR-010 | Functional | Must | The system shall calculate a service-level due date for defined workflow stages. | Expected due dates match the approved rule for representative routine and urgent cases. | Configuration workbook; SQL/Python logic; UAT | Functional test + UAT | Not Started | Not Tested |  | Brandon McDermott
FR-011 | Functional | Must | The system shall flag referrals that exceed their current-stage service level. | A test referral past its due date returns `overdue_flag = 1`. | Configuration workbook; SQL/Python logic; UAT | Functional test + UAT | Not Started | Not Tested |  | Brandon McDermott
FR-012 | Functional | Must | Users shall be able to retrieve new-intake, needs-information, outreach, appointment-verification, report-pending, urgent-escalation, unassigned, and data-exception queues. | Each queue has documented inclusion logic and returns its seeded test cases. | Configuration workbook; SQL/Python logic; UAT | Functional test + UAT | Not Started | Not Tested |  | Brandon McDermott
FR-013 | Functional | Should | Referral managers shall be able to reassign referrals while preserving assignment history. | Reassignment records old owner, new owner, user, timestamp, and reason when required. | Configuration workbook; SQL/Python logic; UAT | Functional test + UAT | Not Started | Not Tested |  | Brandon McDermott
FR-014 | Functional | Must | Users shall record each outreach attempt as a separate event. | Multiple attempts can be stored for one referral without overwriting earlier attempts. | Configuration workbook; SQL/Python logic; UAT | Functional test + UAT | Not Started | Not Tested |  | Brandon McDermott
FR-015 | Functional | Must | Each outreach attempt shall capture timestamp, channel, outcome, and staff member. | These fields are required for all completed outreach events. | Configuration workbook; SQL/Python logic; UAT | Functional test + UAT | Not Started | Not Tested |  | Brandon McDermott
FR-016 | Functional | Should | Outreach attempts shall capture contacted party, next-action date, and optional notes. | Fields are stored and retrievable for representative test events. | Configuration workbook; SQL/Python logic; UAT | Functional test + UAT | Not Started | Not Tested |  | Brandon McDermott
FR-017 | Functional | Must | The system shall calculate attempt count and most recent attempt date. | Derived results match the underlying outreach records. | Configuration workbook; SQL/Python logic; UAT | Functional test + UAT | Not Started | Not Tested |  | Brandon McDermott
FR-018 | Functional | Must | Active outreach referrals shall have a documented next action or approved disposition. | A query identifies referrals lacking both and returns no unresolved critical test cases after remediation. | Configuration workbook; SQL/Python logic; UAT | Functional test + UAT | Not Started | Not Tested |  | Brandon McDermott
FR-019 | Functional | Should | Patient communication preference shall be visible when available. | The preference appears in the referral dataset or work queue without replacing staff judgment. | Configuration workbook; SQL/Python logic; UAT | Functional test + UAT | Not Started | Not Tested |  | Brandon McDermott
FR-020 | Functional | Must | Users shall record specialist, appointment date, location or modality, and scheduling source. | A scheduled referral contains all required appointment fields. | Configuration workbook; SQL/Python logic; UAT | Functional test + UAT | Not Started | Not Tested |  | Brandon McDermott
FR-021 | Functional | Must | Setting an appointment shall change referral status to `Scheduled` but shall not close the referral. | A scheduled test referral remains active and does not meet completed-closure logic. | Configuration workbook; SQL/Python logic; UAT | Functional test + UAT | Not Started | Not Tested |  | Brandon McDermott
FR-022 | Functional | Must | The system shall support completed, cancelled, no-show, rescheduled, and unknown appointment outcomes. | Each seeded outcome is accepted and routed according to the workflow. | Configuration workbook; SQL/Python logic; UAT | Functional test + UAT | Not Started | Not Tested |  | Brandon McDermott
FR-023 | Functional | Must | Elapsed appointments lacking a final outcome shall appear in an appointment-verification queue. | A past appointment with no outcome appears in the queue. | Configuration workbook; SQL/Python logic; UAT | Functional test + UAT | Not Started | Not Tested |  | Brandon McDermott
FR-024 | Functional | Should | Rescheduling shall preserve prior appointment history. | Both original and replacement appointment records remain available. | Configuration workbook; SQL/Python logic; UAT | Functional test + UAT | Not Started | Not Tested |  | Brandon McDermott
FR-025 | Functional | Must | Cancellation and no-show outcomes shall require a next action or approved closure review. | Seeded cancelled and no-show cases cannot disappear from active work without disposition. | Configuration workbook; SQL/Python logic; UAT | Functional test + UAT | Not Started | Not Tested |  | Brandon McDermott
FR-026 | Functional | Must | A completed appointment shall move the referral to `Completed—Report Pending` unless an approved exception applies. | A completed test encounter enters the report-pending workflow. | Configuration workbook; SQL/Python logic; UAT | Functional test + UAT | Not Started | Not Tested |  | Brandon McDermott
FR-027 | Functional | Must | The system shall capture report received date, source, and document identifier. | These values are available for each linked report. | Configuration workbook; SQL/Python logic; UAT | Functional test + UAT | Not Started | Not Tested |  | Brandon McDermott
FR-028 | Functional | Must | A consultation report shall be linked to the originating referral. | The linked referral identifier is non-null, or the report appears in a matching-exception queue. | Configuration workbook; SQL/Python logic; UAT | Functional test + UAT | Not Started | Not Tested |  | Brandon McDermott
FR-029 | Functional | Must | Unmatched or ambiguously matched reports shall require human review. | Seeded ambiguous reports are not automatically attached and appear in the exception queue. | Configuration workbook; SQL/Python logic; UAT | Functional test + UAT | Not Started | Not Tested |  | Brandon McDermott
FR-030 | Functional | Must | Completed visits without reports shall appear in the report-pending queue. | The queue includes all seeded completed visits lacking reports and excludes those with valid reports. | Configuration workbook; SQL/Python logic; UAT | Functional test + UAT | Not Started | Not Tested |  | Brandon McDermott
FR-031 | Functional | Must | `Closed—Completed` shall require a completed encounter, received linked report, report routing, and required clinician review. | A referral missing any required milestone fails completed-closure validation. | Configuration workbook; SQL/Python logic; UAT | Functional test + UAT | Not Started | Not Tested |  | Brandon McDermott
FR-032 | Functional | Must | `Closed—Not Completed` shall require an approved reason and authorized disposition. | A non-completed closure lacking an approved reason is rejected or flagged. | Configuration workbook; SQL/Python logic; UAT | Functional test + UAT | Not Started | Not Tested |  | Brandon McDermott
FR-033 | Functional | Must | Cancellation shall be distinguishable from non-completion. | Cancelled and closed-not-completed are separate status or disposition values. | Configuration workbook; SQL/Python logic; UAT | Functional test + UAT | Not Started | Not Tested |  | Brandon McDermott
FR-034 | Functional | Should | Authorized users shall be able to reopen a terminal referral with a reason. | The action preserves prior closure data and records the user, timestamp, and reason. | Configuration workbook; SQL/Python logic; UAT | Functional test + UAT | Not Started | Not Tested |  | Brandon McDermott
FR-035 | Functional | Must | Every material referral-status change shall create a history record. | Status-history counts and timestamps reconcile with test-case transitions. | Configuration workbook; SQL/Python logic; UAT | Functional test + UAT | Not Started | Not Tested |  | Brandon McDermott
FR-036 | Functional | Must | Status history shall capture prior status, new status, timestamp, and source or user. | All required fields are present for valid history records. | Configuration workbook; SQL/Python logic; UAT | Functional test + UAT | Not Started | Not Tested |  | Brandon McDermott
FR-037 | Functional | Must | Invalid status transitions shall be rejected or flagged. | Representative invalid transitions produce the expected error or exception. | Configuration workbook; SQL/Python logic; UAT | Functional test + UAT | Not Started | Not Tested |  | Brandon McDermott
FR-038 | Functional | Should | Users shall be able to view a chronological referral timeline. | A query or view returns ordered referral events for a selected record. | Configuration workbook; SQL/Python logic; UAT | Functional test + UAT | Not Started | Not Tested |  | Brandon McDermott
DR-001 | Data | Must | The solution shall maintain defined patient, provider, organization, location, payer, specialty, referral, status-history, outreach, appointment, report, and user entities. | The physical schema contains the approved entities and relationships. | Data model; data dictionary; SQL/Python validation | SQL/Python validation | Not Started | Not Tested |  | Brandon McDermott
DR-002 | Data | Must | Primary and foreign keys shall enforce referential integrity. | Orphan-record tests return zero unexplained records after the validated load. | Data model; data dictionary; SQL/Python validation | SQL/Python validation | Not Started | Not Tested |  | Brandon McDermott
DR-003 | Data | Must | Controlled workflow values shall use reference tables or enforceable constraints. | Invalid statuses, priorities, appointment outcomes, and closure reasons are rejected or captured as exceptions. | Data model; data dictionary; SQL/Python validation | SQL/Python validation | Not Started | Not Tested |  | Brandon McDermott
DR-004 | Data | Must | The database shall preserve source identifiers and source-system attribution. | Migrated records can be traced from target to source. | Data model; data dictionary; SQL/Python validation | SQL/Python validation | Not Started | Not Tested |  | Brandon McDermott
DR-005 | Data | Must | Required timestamps shall use one documented time-zone convention. | The data dictionary identifies the convention and validation finds no invalid timestamp formats. | Data model; data dictionary; SQL/Python validation | SQL/Python validation | Not Started | Not Tested |  | Brandon McDermott
DR-006 | Data | Must | Raw, transformed, and analytical data shall remain distinguishable. | Separate files, schemas, tables, or documented layers exist for each stage. | Data model; data dictionary; SQL/Python validation | SQL/Python validation | Not Started | Not Tested |  | Brandon McDermott
DR-007 | Data | Must | Migration validation shall reconcile source and target record counts. | Counts are documented by entity, including accepted, rejected, and exception records. | Data model; data dictionary; SQL/Python validation | SQL/Python validation | Not Started | Not Tested |  | Brandon McDermott
DR-008 | Data | Must | Migration validation shall check required fields, duplicates, referential integrity, allowed values, and date logic. | Each check has a reproducible SQL or Python result. | Data model; data dictionary; SQL/Python validation | SQL/Python validation | Not Started | Not Tested |  | Brandon McDermott
DR-009 | Data | Must | Synthetic data shall include realistic exceptions and workflow variation. | The dataset contains documented missing, duplicate, late, cancelled, no-show, unmatched, and overdue cases. | Data model; data dictionary; SQL/Python validation | SQL/Python validation | Not Started | Not Tested |  | Brandon McDermott
DR-010 | Data | Must | No real patient data or PHI shall appear in the project. | Manual review and automated scans find no known real patient identifiers or credentials. | Data model; data dictionary; SQL/Python validation | SQL/Python validation | Not Started | Not Tested |  | Brandon McDermott
DR-011 | Data | Should | Analytical fields shall be reproducible from documented source fields and logic. | Each derived KPI field has a definition or transformation rule. | Data model; data dictionary; SQL/Python validation | SQL/Python validation | Not Started | Not Tested |  | Brandon McDermott
DR-012 | Data | Should | Date logic shall reject impossible sequences. | Tests identify cases such as report receipt before encounter completion or closure before referral receipt. | Data model; data dictionary; SQL/Python validation | SQL/Python validation | Not Started | Not Tested |  | Brandon McDermott
IR-001 | Integration | Must | The project shall document source-to-target mappings for referral data. | Every required target field maps to a source field, default, transformation, or documented gap. | Source-to-target mapping; FHIR JSON; Postman tests | API test + document review | Not Started | Not Tested |  | Brandon McDermott
IR-002 | Integration | Must | Representative referral information shall map to selected FHIR R4 resources. | The mapping covers `Patient`, `Practitioner`, `Organization`, `ServiceRequest`, `Task`, `Appointment`, and a report resource. | Source-to-target mapping; FHIR JSON; Postman tests | API test + document review | Not Started | Not Tested |  | Brandon McDermott
IR-003 | Integration | Must | FHIR JSON examples shall use syntactically valid JSON and documented identifiers or references. | JSON parsing succeeds and internal references resolve within each test bundle or documented server context. | Source-to-target mapping; FHIR JSON; Postman tests | API test + document review | Not Started | Not Tested |  | Brandon McDermott
IR-004 | Integration | Must | Postman tests shall demonstrate representative create or update and retrieval behavior. | The collection records expected successful responses for the defined positive tests. | Source-to-target mapping; FHIR JSON; Postman tests | API test + document review | Not Started | Not Tested |  | Brandon McDermott
IR-005 | Integration | Must | API testing shall include negative cases. | Missing required data, invalid references, or invalid values produce documented failure behavior. | Source-to-target mapping; FHIR JSON; Postman tests | API test + document review | Not Started | Not Tested |  | Brandon McDermott
IR-006 | Integration | Must | Integration failures shall be traceable to a source transaction or referral. | Error records include source identifier, timestamp, error category, and status. | Source-to-target mapping; FHIR JSON; Postman tests | API test + document review | Not Started | Not Tested |  | Brandon McDermott
IR-007 | Integration | Should | Retryable and non-retryable integration failures shall be distinguishable. | Error-handling documentation assigns representative failures to the correct category. | Source-to-target mapping; FHIR JSON; Postman tests | API test + document review | Not Started | Not Tested |  | Brandon McDermott
IR-008 | Integration | Must | The documentation shall state that the FHIR demonstration is not a production interface or certification. | The limitation appears in the FHIR documentation and README. | Source-to-target mapping; FHIR JSON; Postman tests | API test + document review | Not Started | Not Tested |  | Brandon McDermott
RR-001 | Reporting & Analytics | Must | Every KPI shall have a documented definition, numerator, denominator, exclusions, date field, and null-handling rule. | The metric specification contains all required components before dashboard publication. | Metric specification; SQL views; Tableau validation | SQL reconciliation + dashboard QA | Not Started | Not Tested |  | Brandon McDermott
RR-002 | Reporting & Analytics | Must | The dashboard shall display referral volume, intake completeness, scheduling conversion, appointment completion, closed-loop rate, cycle times, no-show rate, and overdue open referrals. | Each KPI is present and reconciles to its approved SQL result. | Metric specification; SQL views; Tableau validation | SQL reconciliation + dashboard QA | Not Started | Not Tested |  | Brandon McDermott
RR-003 | Reporting & Analytics | Must | The dashboard shall show the referral funnel by meaningful workflow stage. | Funnel counts follow governed stage definitions and do not double-count referrals. | Metric specification; SQL views; Tableau validation | SQL reconciliation + dashboard QA | Not Started | Not Tested |  | Brandon McDermott
RR-004 | Reporting & Analytics | Must | Users shall be able to analyze performance by site, specialty, payer, provider, priority, status, and referral month where data permit. | Filters return expected representative subsets. | Metric specification; SQL views; Tableau validation | SQL reconciliation + dashboard QA | Not Started | Not Tested |  | Brandon McDermott
RR-005 | Reporting & Analytics | Must | The dashboard shall contain an actionable overdue-referral work queue. | The queue includes referral identifier, stage, owner, urgency, age, due date, and reason for inclusion. | Metric specification; SQL views; Tableau validation | SQL reconciliation + dashboard QA | Not Started | Not Tested |  | Brandon McDermott
RR-006 | Reporting & Analytics | Must | Dashboard calculations shall use reusable SQL views or documented transformations. | Published metrics can be reproduced outside Tableau. | Metric specification; SQL views; Tableau validation | SQL reconciliation + dashboard QA | Not Started | Not Tested |  | Brandon McDermott
RR-007 | Reporting & Analytics | Must | KPI validation shall compare Tableau outputs with independent SQL results. | Differences are zero or documented and resolved before publication. | Metric specification; SQL views; Tableau validation | SQL reconciliation + dashboard QA | Not Started | Not Tested |  | Brandon McDermott
RR-008 | Reporting & Analytics | Should | The dashboard shall distinguish simulated baseline and post-redesign scenarios without implying real-world causality. | Scenario labels and methodology notes appear in the dashboard or README. | Metric specification; SQL views; Tableau validation | SQL reconciliation + dashboard QA | Not Started | Not Tested |  | Brandon McDermott
RR-009 | Reporting & Analytics | Should | Small-cell or privacy-sensitive reporting considerations shall be documented even though data are synthetic. | Reporting documentation states how suppression or access controls would be handled in production. | Metric specification; SQL views; Tableau validation | SQL reconciliation + dashboard QA | Not Started | Not Tested |  | Brandon McDermott
SR-001 | Security, Privacy & Audit | Must | The proposed design shall use role-based access concepts. | A role-permission matrix defines representative access for each user type. | Role-permission matrix; audit design; repository QA | Control review + negative test | Not Started | Not Tested |  | Brandon McDermott
SR-002 | Security, Privacy & Audit | Must | Access shall follow a minimum-necessary principle. | Each role has only the permissions needed for its stated duties. | Role-permission matrix; audit design; repository QA | Control review + negative test | Not Started | Not Tested |  | Brandon McDermott
SR-003 | Security, Privacy & Audit | Must | Material workflow changes shall be attributable to a user or system source. | Audit fields exist for status, assignment, override, and closure actions. | Role-permission matrix; audit design; repository QA | Control review + negative test | Not Started | Not Tested |  | Brandon McDermott
SR-004 | Security, Privacy & Audit | Must | Overrides and terminal-status changes shall require a documented reason where defined. | Test records missing required reasons fail validation. | Role-permission matrix; audit design; repository QA | Control review + negative test | Not Started | Not Tested |  | Brandon McDermott
SR-005 | Security, Privacy & Audit | Must | The public repository shall contain only synthetic, nonconfidential data and nonsecret configuration. | Repository review finds no PHI, passwords, access tokens, private keys, or live credentials. | Role-permission matrix; audit design; repository QA | Control review + negative test | Not Started | Not Tested |  | Brandon McDermott
SR-006 | Security, Privacy & Audit | Should | Production security considerations shall include authentication, authorization, encryption, logging, retention, and incident response. | The architecture or security notes address all six areas as future production requirements. | Role-permission matrix; audit design; repository QA | Control review + negative test | Not Started | Not Tested |  | Brandon McDermott
SR-007 | Security, Privacy & Audit | Should | Analytical access shall be separated conceptually from operational write access. | The role model gives analysts approved read access without routine workflow-update privileges. | Role-permission matrix; audit design; repository QA | Control review + negative test | Not Started | Not Tested |  | Brandon McDermott
NFR-001 | Nonfunctional | Must | The MVP shall run using Mac-compatible and accessible tools. | Core deliverables run in MySQL Workbench, Python, Postman, Tableau Public, VS Code, and GitHub. | README; reproducibility test; technical QA | Technical review | Not Started | Not Tested |  | Brandon McDermott
NFR-002 | Nonfunctional | Must | SQL, Python, JSON, and documentation shall be reproducible from repository instructions. | A reviewer can follow the README to reproduce the core data and analytical workflow. | README; reproducibility test; technical QA | Technical review | Not Started | Not Tested |  | Brandon McDermott
NFR-003 | Nonfunctional | Must | Naming conventions shall be consistent across datasets, database objects, code, and documentation. | QA finds no unexplained conflicting names for core entities or fields. | README; reproducibility test; technical QA | Technical review | Not Started | Not Tested |  | Brandon McDermott
NFR-004 | Nonfunctional | Should | Queries and views shall complete within a reasonable time for approximately 2,500 referrals and their related events. | Core analytical queries execute without material delay in the portfolio environment. | README; reproducibility test; technical QA | Technical review | Not Started | Not Tested |  | Brandon McDermott
NFR-005 | Nonfunctional | Must | Errors shall be understandable and traceable. | Data and API exception outputs identify the affected record and rule or error category. | README; reproducibility test; technical QA | Technical review | Not Started | Not Tested |  | Brandon McDermott
NFR-006 | Nonfunctional | Must | Documentation shall distinguish implemented behavior, simulated behavior, assumptions, and future production needs. | README and major deliverables use explicit labels consistently. | README; reproducibility test; technical QA | Technical review | Not Started | Not Tested |  | Brandon McDermott
NFR-007 | Nonfunctional | Should | Workflow and dashboard outputs shall be understandable to both operational and technical reviewers. | UAT or structured review confirms that key actions and metric definitions can be identified without source-code inspection. | README; reproducibility test; technical QA | Technical review | Not Started | Not Tested |  | Brandon McDermott
IMR-001 | Implementation & Support | Must | Requirements shall be traceable to configuration, code, documentation, or tests. | A traceability matrix contains every Must requirement and its verification method. | Implementation artifacts; UAT; go-live documentation | Document review + readiness test | Not Started | Not Tested |  | Brandon McDermott
IMR-002 | Implementation & Support | Must | The implementation shall maintain a configuration workbook. | Statuses, queues, controlled values, service levels, and selected business rules are documented. | Implementation artifacts; UAT; go-live documentation | Document review + readiness test | Not Started | Not Tested |  | Brandon McDermott
IMR-003 | Implementation & Support | Must | Data migration shall include pre-load, load, and post-load validation. | The migration report records results for all three stages. | Implementation artifacts; UAT; go-live documentation | Document review + readiness test | Not Started | Not Tested |  | Brandon McDermott
IMR-004 | Implementation & Support | Must | UAT shall include positive, negative, boundary, and end-to-end referral scenarios. | The UAT plan contains all four test categories. | Implementation artifacts; UAT; go-live documentation | Document review + readiness test | Not Started | Not Tested |  | Brandon McDermott
IMR-005 | Implementation & Support | Must | Critical workflow scenarios shall pass before go-live readiness is declared. | No open critical defects remain, or a formal non-go-live decision is documented. | Implementation artifacts; UAT; go-live documentation | Document review + readiness test | Not Started | Not Tested |  | Brandon McDermott
IMR-006 | Implementation & Support | Must | Defects shall record severity, owner, status, evidence, resolution, and retest result. | Every logged defect contains all required fields. | Implementation artifacts; UAT; go-live documentation | Document review + readiness test | Not Started | Not Tested |  | Brandon McDermott
IMR-007 | Implementation & Support | Must | Training shall be role-based. | Referral coordinators, managers, clinicians, and support staff have distinct learning objectives or materials. | Implementation artifacts; UAT; go-live documentation | Document review + readiness test | Not Started | Not Tested |  | Brandon McDermott
IMR-008 | Implementation & Support | Must | The go-live runbook shall include readiness checks, cutover steps, validation, rollback, support, and escalation. | All six sections are present and assigned. | Implementation artifacts; UAT; go-live documentation | Document review + readiness test | Not Started | Not Tested |  | Brandon McDermott
IMR-009 | Implementation & Support | Should | The implementation shall define post-launch adoption and performance monitoring. | The support plan includes queue usage, data quality, defects, KPI stability, and user feedback. | Implementation artifacts; UAT; go-live documentation | Document review + readiness test | Not Started | Not Tested |  | Brandon McDermott
IMR-010 | Implementation & Support | Must | Scope changes and key design decisions shall be documented. | A decision log or change log records the date, decision, rationale, owner, and affected deliverables. | Implementation artifacts; UAT; go-live documentation | Document review + readiness test | Not Started | Not Tested |  | Brandon McDermott
IMR-011 | Implementation & Support | Must | The final portfolio README shall explain the problem, approach, solution, validation, findings, limitations, and how to reproduce the work. | All sections are present and linked to supporting artifacts. | Implementation artifacts; UAT; go-live documentation | Document review + readiness test | Not Started | Not Tested |  | Brandon McDermott
IMR-012 | Implementation & Support | Must | The public case study shall not describe simulated improvements as actual client outcomes. | QA review confirms that all modeled results are labeled as synthetic or scenario-based. | Implementation artifacts; UAT; go-live documentation | Document review + readiness test | Not Started | Not Tested |  | Brandon McDermott

## Status Summary
Project 4 — RTM Status Summary
Formula-driven overview; update statuses in the Requirements RTM tab
Portfolio Control | Value
Total requirements | 101
Must requirements | 82
Implemented | 0
Tests passed | 0
Requirement Type | Total | Implemented | Passed
Business | 8 | 0 | 0
Functional | 38 | 0 | 0
Data | 12 | 0 | 0
Integration | 8 | 0 | 0
Reporting & Analytics | 9 | 0 | 0
Security, Privacy & Audit | 7 | 0 | 0
Nonfunctional | 7 | 0 | 0
Implementation & Support | 12 | 0 | 0

## Lists
Controlled Values and Workbook Instructions
Field | Controlled values / instructions
Implementation Status | Not Started; In Progress; Implemented; Deferred; Not Applicable
Test Status | Not Tested; Pass; Fail; Blocked; Not Applicable
Priority | Must; Should; Could
Evidence Path / Link | Enter the repository-relative path or a durable link to the artifact proving the requirement.
Notes | Record exceptions, decisions, blockers, scope changes, or future-production limitations.