## UAT Summary
UAT Summary
Formula-driven UAT readiness and release gate. Results update as Test Cases and Defect Log are completed.
Total Tests | Passed | Failed | Blocked | Not Run | Pass Rate | Critical Pass Rate | Release Gate
30 | 4 | 0 | 0 | 26 | 100% | 11.76% | NOT READY
Defect Gate |  |  |  |  | Release Acceptance Criteria
Measure | Value |  |  |  | Criterion | Threshold | Current
Open Critical Defects | 0 |  |  |  | Overall pass rate | 95% | 100%
Open High Defects | 0 |  |  |  | Critical pass rate | 100% | 11.76%
All Open Defects | 0 |  |  |  | Open critical defects | 0 | 0
[5 empty] | Open high defects | 0 | 0
[5 empty] | Incomplete tests | 0 | 26
Execution guidance: record Actual Result, Evidence Link, tester, date, and any Defect ID for every executed test. Do not mark a test Pass without objective evidence.

## Test Cases
Test Cases
Executable acceptance tests mapped to requirements and configuration controls. Yellow fields are completed during UAT execution.
Test ID | Domain | Priority | Test Scenario | Preconditions | Test Steps | Expected Result | Requirement ID | Configuration Reference | Execution Status | Actual Result | Defect ID | Tester | Execution Date | Evidence Link | Comments
UAT-001 | Workflow | Critical | Create a valid routine referral | Valid patient, provider, specialty, payer, and required intake fields | 1. Create referral; 2. Save; 3. Open lifecycle | Referral ID is generated; status = Received; audit event created | REQ-F01 | STS-01 | Not Run
UAT-002 | Workflow | Critical | Route complete referral to outreach | Referral in Received with all required fields | 1. Run intake validation; 2. Confirm result | Status changes to Ready for Outreach; queue = Ready for Outreach | REQ-F02 | STS-03 / QUE-03 | Not Run
UAT-003 | Workflow | Critical | Route incomplete referral to Needs Information | Referral missing required insurance or clinical field | 1. Run validation; 2. Review issue | Status = Needs Information; blocking issue is recorded | REQ-F03 | STS-02 / QUE-02 | Not Run
UAT-004 | Workflow | High | Resolve missing information | Referral in Needs Information with open issue | 1. Correct field; 2. Resolve issue; 3. Revalidate | Issue closes; referral advances to Ready for Outreach | REQ-F04 | TRN-04 | Not Run
UAT-005 | Outreach | Critical | Record first outreach attempt | Referral in Ready for Outreach | 1. Add channel, party, outcome, timestamp; 2. Save | Attempt is saved; status = Outreach in Progress; next action calculated | REQ-F05 | OUT-01–OUT-09 | Not Run
UAT-006 | Outreach | High | Require next action for No Answer | Outcome = No Answer | 1. Record No Answer; 2. Attempt save without next action | System requires next action; default target = 48 hours | REQ-F06 | OUT-02 | Not Run
UAT-007 | Outreach | High | Escalate invalid contact information | Outcome = Invalid Contact | 1. Record outcome; 2. Save | Data exception/escalation created; next action due within 24 hours | REQ-F07 | OUT-04 | Not Run
UAT-008 | Scheduling | Critical | Create appointment | Referral in outreach; valid specialist and location | 1. Enter appointment details; 2. Confirm | Appointment saved; referral status = Scheduled | REQ-F08 | STS-05 | Not Run
UAT-009 | Scheduling | High | Reject appointment before scheduled timestamp | Appointment start precedes scheduled_at | 1. Enter invalid timestamps; 2. Save | Save is blocked with clear validation message | REQ-N01 | DQ-013 | Not Run
UAT-010 | Scheduling | High | Route cancelled appointment to follow-up | Scheduled referral with cancelled appointment | 1. Record cancellation; 2. select follow-up required | Referral returns to Outreach in Progress with reason | REQ-F09 | TRN-14 | Not Run
UAT-011 | Scheduling | Critical | Record completed appointment | Scheduled referral with elapsed appointment | 1. Mark Completed; 2. record outcome time | Referral status = Completed—Report Pending | REQ-F10 | TRN-15 | Not Run
UAT-012 | Report | Critical | Match consult report to referral | Unmatched report with valid identifiers | 1. Run match; 2. confirm referral link | Report is Matched and linked to referral | REQ-F11 | DQ-016 | Not Run
UAT-013 | Report | Critical | Route and review consult report | Matched report; reviewer authorized | 1. Route; 2. review; 3. record timestamps | Report = Reviewed; reviewer recorded; referral = Closed—Completed | REQ-F12 | TRN-18 | Not Run
UAT-014 | Report | High | Reject review without reviewer | Report marked Reviewed without reviewer ID | 1. attempt save | Save is blocked; reviewer and review timestamp required | REQ-N02 | DQ-017 | Not Run
UAT-015 | Closure | Critical | Close referral as patient declined | Documented decline; manager user | 1. choose Patient Declined; 2. approve closure | Referral = Closed—Not Completed; reason and approver audited | REQ-F13 | CLR-02 | Not Run
UAT-016 | Closure | Critical | Prevent unauthorized noncompletion closure | Coordinator without manager rights | 1. attempt Closed—Not Completed | Transition is denied; no status change occurs | REQ-S01 | Roles Permissions | Not Run
UAT-017 | Closure | High | Cancel duplicate referral | Known duplicate referral ID | 1. choose Duplicate Referral; 2. enter duplicate ID | Referral = Cancelled; duplicate ID retained | REQ-F14 | CLR-07 | Not Run
UAT-018 | SLA | Critical | Apply urgent intake SLA | New urgent referral | 1. create referral; 2. inspect due time | Service-level due time = received_at + 8 calendar hours | REQ-F15 | SLA-02 | Not Run
UAT-019 | SLA | High | Apply routine outreach SLA | Routine referral becomes Ready for Outreach | 1. inspect due time | Initial outreach due = status entry + 72 calendar hours | REQ-F16 | SLA-03 | Not Run
UAT-020 | SLA | High | Escalate overdue urgent referral | Urgent open referral past due | 1. refresh work queue | Referral appears in Urgent Escalations and sorts by most overdue | REQ-F17 | QUE-07 | Not Run
UAT-021 | Queue | Critical | Display all unassigned open referrals | Open referral without active assignment | 1. refresh Unassigned Referrals | Referral appears once and displays recommended action | REQ-F18 | QUE-08 / DQ-011 | Not Run
UAT-022 | Queue | High | Display elapsed appointment verification work | Scheduled referral with appointment in past | 1. refresh queue | Referral appears in Appointment Verification | REQ-F19 | QUE-05 | Not Run
UAT-023 | Permissions | Critical | Coordinator cannot configure workflow rules | Referral Coordinator user | 1. open configuration; 2. attempt edit | Configuration is read-only or inaccessible | REQ-S02 | Roles Permissions | Not Run
UAT-024 | Permissions | Critical | System Administrator can configure rules but not clinical review | System Administrator user | 1. edit config; 2. attempt report review | Config edit succeeds; clinical report review is denied | REQ-S03 | Roles Permissions | Not Run
UAT-025 | Audit | Critical | Preserve lifecycle history | Referral advances through at least three statuses | 1. open audit history | All transitions show old/new state, timestamp, actor, and reason | REQ-A01 | DQ-009 / DQ-010 | Not Run
UAT-026 | Data Quality | Critical | Execute 20-rule data-quality suite | Database loaded with validated synthetic data | 1. run data_quality_checks.sql | 20 tested; 20 passed; 0 failed; total failures = 0 | REQ-DQ01 | DQ-001–DQ-020 | Pass | 20 rules tested; 20 passed; 0 failed; 0 total failures. |  | Brandon McDermott | 2026-08-17 | images/uat_026_data_quality_results.png | Results match the acceptance criteria.
UAT-027 | Analytics | Critical | Reconcile referral total | Operational views created | 1. query lifecycle view; 2. compare base table | Lifecycle view returns 2,500 referrals | REQ-R01 | v_referral_lifecycle | Pass | v_referral_lifecycle returned 2,500 rows. |  | Brandon McDermott | 2026-08-17 | images/uat_027_lifecycle_count.png | Result reconciles to the 2,500 base referrals.
UAT-028 | Analytics | High | Reconcile open work queue | Operational views created | 1. count work queue rows | Work queue returns 965 open referrals | REQ-R02 | v_operational_work_queue | Pass | v_operational_work_queue returned 965 rows. |  | Brandon McDermott | 2026-08-17 | images/uat_028_work_queue_count.png | Result matches the expected open-referral population.
UAT-029 | Analytics | High | Reconcile executive KPI rates | Analytics queries executed | 1. run executive KPI query | Completeness 94.36%; scheduling 77.48%; completion 79.12%; closed-loop 45.92% | REQ-R03 | analytics_queries.sql | Pass | KPI query returned 2,500 total, 314 urgent, 965 open, and 965 overdue open referrals; calculated rates and averages matched expected results. |  | Brandon McDermott | 2026-08-17 | images/uat_029_executive_kpis.png | Executive KPI results match the validated baseline.
UAT-030 | Integration | High | Reject duplicate external consult document | Existing external_document_id | 1. load same document ID again | Duplicate is rejected or safely marked Duplicate without a second active record | REQ-I01 | uq_consult_reports_external_id | Not Run |  |  | Brandon McDermott | 2026-08-17

## Defect Log
Defect Log
Log UAT defects, resolution ownership, retest results, and release-blocking decisions.
Defect ID | Test ID | Title | Description | Severity | Status | Owner | Date Found | Target Fix Date | Resolution | Retest Status | Retest Date | Evidence Link
DEF-001
DEF-002
DEF-003
DEF-004
DEF-005
DEF-006
DEF-007
DEF-008
DEF-009
DEF-010
DEF-011
DEF-012
DEF-013
DEF-014
DEF-015

## Signoff
Signoff
Formal release recommendation and stakeholder approval record. Complete only after test execution and defect review.
Role | Name | Decision | Signature / Approval Evidence | Decision Date | Conditions | Open Risk Accepted? | Comments
Referral Operations Lead |  | Pending |  |  |  | No
Clinical Representative |  | Pending |  |  |  | No
Health IT / Technical Lead |  | Pending |  |  |  | No
Implementation Lead |  | Pending |  |  |  | No
Executive Sponsor |  | Pending |  |  |  | No

## Reference Values
Reference Values
Controlled execution values and release acceptance thresholds used by the workbook.
Category | Value | Definition | Release Effect
Execution Status | Not Run | Test has not been executed | Incomplete
Execution Status | Pass | Observed result matches expected result | Acceptable
Execution Status | Fail | Observed result does not match expected result | Requires defect
Execution Status | Blocked | Execution prevented by dependency or environment | Incomplete
Execution Status | N/A | Approved as outside release scope | Excluded
Priority | Critical | Core workflow, security, data integrity, or release-blocking function | Must pass
Priority | High | Material operational function | Must pass or have approved workaround
Priority | Medium | Useful function with limited operational impact | Risk acceptance possible
Priority | Low | Minor or cosmetic behavior | May defer
Acceptance | Overall pass rate | >= 95% of executed in-scope tests | Required
Acceptance | Critical pass rate | 100% | Required
Acceptance | Open critical defects | 0 | Required
Acceptance | Open high defects | 0 unless formally accepted | Required